EDUBRIDGE

Software Project Management Plan

Professional Scope Report

Structured in alignment with ISO/IEC/IEEE 16326:2019 and tailored to the scope, duration, resources, and academic nature of the EduBridge project.

| Document Item | Details |
| --- | --- |
| Document ID | EDU-SPMP-001 |
| Version / Status | 1.0 / Proposed |
| Prepared For | Dr. Umer Rashid |
| Prepared By | Eishaal Naeem, Hansa Nawal, Laiba Khan |
| Planned Duration | Eight weeks |
| Reference Document | EduBridge Software Requirements Specification |
| Applicable Standard | ISO/IEC/IEEE 16326:2019 |

# 1. Project Overview

## 1.1 Project Summary

EduBridge is a web-based educational platform integrating tutor discovery, course delivery, assignment bidding, live interactive sessions, parent monitoring, and secure payment processing. It supports Students, Tutors, Parents, and Administrators through a three-tier architecture comprising presentation, application, and data layers.

## 1.2 Purpose, Scope and Objectives

### Purpose

To provide a secure, centralized learning environment where students can find tutors, enroll in courses, post assignments, receive bids, attend live sessions, and make traceable payments.

### Scope

User registration, authentication, and role-based access control.

Tutor search, filtering, ratings, and recommendations.

Course creation, resource upload, enrollment, and progress monitoring.

Assignment posting, tutor bidding, bid selection, and project activation.

Live-session scheduling, reminders, audio/video interaction, and screen sharing.

Secure payment processing, receipts, transaction history, parent monitoring, administration, and audit logging.

### Out of Scope

Custom payment-gateway or video-streaming infrastructure.

Native mobile applications and physical classroom management.

Production-scale testing with 10,000 actual concurrent users.

Formal ISO certification. External services may be integrated or simulated for academic demonstration.

### Objectives and Success Criteria

Implement all critical workflows and enforce role-specific access.

Deliver an integrated, tested prototype within eight weeks.

Complete the required project, testing, user, and deployment documentation.

Achieve acceptance with no unresolved critical defects and a successful final demonstration.

## 1.3 Assumptions and Constraints

| Assumptions | Constraints |
| --- | --- |
| Users have internet-enabled devices, modern browsers, and valid account information. | Eight-week duration and a three-member academic team. |
| Test environments are available for payment, email, hosting, and live-session services. | Live sessions and external services depend on network and third-party availability. |
| Team members have suitable development equipment and shared repository access. | Personal and financial information requires strong access control and protection. |
| A local or cloud test environment is available. | Full production-scale load testing is outside available academic resources. |

## 1.4 Project Deliverables

| ID | Deliverable | Completion Criterion |
| --- | --- | --- |
| D01 | Project Management Plan | Reviewed and baselined |
| D02 | Updated SRS and traceability matrix | Requirements clarified and mapped |
| D03 | UML, DFD, architecture, and database design | Major structures and interactions approved |
| D04 | Interface prototype | Principal screens reviewed |
| D05 | Authentication and RBAC module | Registration, login, and authorization tested |
| D06 | Tutor, course, and assignment modules | Core workflows demonstrated |
| D07 | Payment, session, parent, and admin functions | Approved scenarios demonstrated |
| D08 | Integrated system | Modules combined successfully |
| D09 | Test plan, test report, and user manual | Evidence complete |
| D10 | Deployment package and presentation | Final release delivered |

## 1.5 Schedule Summary

| Phase | Duration | Main Output |
| --- | --- | --- |
| Initiation and Requirements | Week 1 | Approved plan and requirement baseline |
| Architecture and Design | Week 2 | UML, database, and interface designs |
| Core Development | Weeks 3–4 | Authentication, tutor, and course modules |
| Advanced Development | Weeks 5–6 | Assignment, payment, and session modules |
| Integration and Testing | Week 7 | Tested integrated system |
| Deployment and Closure | Week 8 | Final release, manual, and presentation |

# 2. References

ISO/IEC/IEEE 16326:2019, Systems and software engineering: Life cycle processes: Project management.

ISO/IEC/IEEE 12207, Software life cycle processes.

ISO/IEC/IEEE 15288, System life cycle processes.

Pressman, R. S., Software Engineering: A Practitioner’s Approach.

Course lectures and laboratory instructions for Analysis and Design for Software Systems.

# 3. Definitions

| Term | Definition |
| --- | --- |
| EduBridge | Integrated tutoring, course, assignment, live-session, and payment platform. |
| SRS | Software Requirements Specification. |
| SPMP | Software Project Management Plan. |
| LMS | Learning Management System. |
| RBAC | Access control based on assigned user roles. |
| Escrow | Payment held until defined conditions are met. |
| Bid | A tutor’s proposal and price for an assignment. |
| Baseline | An approved version placed under change control. |
| Verification | Confirmation that a work product meets its specification. |
| Validation | Confirmation that the system satisfies intended user needs. |
| Change Request | Formal proposal to modify an approved item. |
| Configuration Item | A controlled document, model, code unit, script, or release component. |

# 4. Project Context

## 4.1 Process Model

EduBridge will use an Incremental Agile process. Each increment will be planned, designed, developed, reviewed, and tested before final integration. This supports parallel work, early feedback, and controlled changes within a small academic team.

| Increment | Functions |
| --- | --- |
| 1 | Registration, authentication, RBAC, and user profiles |
| 2 | Tutor discovery, ratings, courses, and enrollment |
| 3 | Assignment posting, bidding, and bid acceptance |
| 4 | Payments, live sessions, parent monitoring, and administration |
| 5 | Integration, acceptance testing, deployment, and documentation |

## 4.2 Methods, Tools and Techniques

| Area | Selection |
| --- | --- |
| Methods | Object-Oriented Analysis and Design, modular development, traceability, peer review |
| Modeling | Draw.io or Visual Paradigm |
| Interface Design | Figma |
| Development | Visual Studio Code |
| Version Control | Git and GitHub |
| Database | MySQL |
| Documentation | Microsoft Word |
| Techniques | Feature branching, code review, unit, integration, system, and acceptance testing |

## 4.3 Product Acceptance Plan

The course instructor provides final academic acceptance. Internal acceptance occurs after verification, validation, and closure of all critical defects.

| Acceptance Area | Criterion |
| --- | --- |
| Authentication and RBAC | Valid users can authenticate and access only permitted functions. |
| Tutor and Course Functions | Search, filtering, course creation, resource upload, and enrollment operate correctly. |
| Assignment Marketplace | Students post tasks; tutors bid; students select bids. |
| Payments and Sessions | A test transaction is recorded and scheduled-session access is demonstrated. |
| Monitoring and Security | Parent/admin functions, protected communication, and audit records are demonstrated. |
| Documentation and Defects | Required evidence is complete and no critical defect remains open. |